## Cover
Cover
#003e83
#0085f0
#2cdcff
Project Schedule
|  | Project Code | P001
|  | Project Name | Truyenthieu
|  | Project Manager | DuongNH
System ID
System Name
|  | Creator | DuongNH
|  | Created Date | 2026-07-17

## Detail plan
|  |  | DETAIL PLAN | [7 empty] | Mã số: BM05-QT-OP-01
Ngày hiệu lực: 01/04/2025
Lần ban hành: 01
ID | Stage | Task |  |  | PIC | Priority | Plan |  | Actual |  | Effort (PD) |  | Progress (%) | Status | Note | 2025/01 | [30 empty] | 2025/02 | [27 empty] | 2025/03
|  | L1 | L2 | L3 |  |  | Start date | End date | Start date | End date | Plan | Actual | time axis 2025-01-01 to 2025-04-01
1 | System investigation |  |  |  | Dương | [8 empty] | In-progress
2 |  | Khởi động và xác định phạm vi |  |  | Dương | High | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-18 | 1 | 3 | 100% | Done
3 |  | Định nghĩa yêu cầu |  |  | Dương | High | 2026-07-18 | 2026-07-18 |  |  | 1 |  |  | In-progress
4 |  |  | Viết tài liệu Requirement Definition. |  | Dương | High | 2026-07-18 | 2026-07-18 | [5 empty] | In-progress
5 | Design |  |  |  | Dương
6 |  | Phân tích nghiệp vụ và thiết kế màn hình |  |  | Dương |  | 2026-07-19 | 2026-07-19 |  |  | 1
7 |  |  | Vẽ figma design |  | Dương | High
8 |  | Làm tài liệu thiết kế |  |  | Dương |  | 2026-07-20 | 2026-07-20 |  |  | 1
9 |  |  | Viết tài liệu FSD |  | Dương | Medium
10 |  | Basic Design |  |  | Dương |  | 2026-07-21 | 2026-07-21 |  |  | 1
11 |  |  | API Design |  | Dương | High
12 |  |  | Database Design |  | Dương | Medium
13 | Coding |  |  |  | Dương
14 |  | Coding backend |  |  | Dương |  | 2026-07-22 | 2026-07-22 |  |  | 1
15 |  |  | Cập nhật database. |  | Dương | High
16 |  |  | API CRUD sách. |  | Dương | High
17 |  |  | Upload PDF. |  | Dương | High
18 |  |  | API đọc/download PDF. |  | Dương | High
19 |  |  | Xóa file khi xóa sách. |  | Dương | High
20 |  |  | Validation file. |  | Dương | High
21 |  |  | Global exception handler. |  | Dương | Medium
22 |  | Coding frontend — quản lý sách |  |  | Dương |  | 2026-07-23 | 2026-07-23 |  |  | 1
23 |  |  | Form thêm/sửa sách. |  | Dương | High
24 |  |  | Upload PDF. |  | Dương | High
25 |  |  | Nhập URL. |  | Dương | High
26 |  |  | Danh sách sách. |  | Dương | High
27 |  |  | Tìm kiếm, lọc và sắp xếp. |  | Dương | High
28 |  |  | Yêu thích và trạng thái đọc. |  | Dương | High
29 |  |  | Xử lý loading và lỗi. |  | Dương | High
30 |  | Coding frontend — đọc PDF |  |  | Dương |  | 2026-07-24 | 2026-07-24 |  |  | 1
31 |  |  | Đọc PDF từ backend. |  | Dương | High
32 |  |  | Đọc PDF từ URL. |  | Dương | High
33 |  |  | Chuyển trang. |  | Dương | High
34 |  |  | Zoom. |  | Dương | High
35 |  |  | Nhảy đến trang. |  | Dương | High
36 |  |  | Lưu trang gần nhất. |  | Dương | High
37 |  |  | Giao diện responsive. |  | Dương | High
38 |  | Coding offline và hoàn thiện |  |  | Dương |  | 2026-07-25 | 2026-07-25 |  |  | 1
39 |  |  | Tải PDF vào IndexedDB. |  | Dương | High
40 |  |  | Ưu tiên đọc bản offline. |  | Dương | High
41 |  |  | Xóa bản offline. |  | Dương | High
42 |  |  | Hiển thị trạng thái đã tải. |  | Dương | High
43 |  |  | Kiểm tra mất mạng. |  | Dương | High
44 |  |  | Hoàn thiện thông báo lỗi. |  | Dương | High
45 | Testing |  |  |  | Dương |  | 2026-07-26 | 2026-07-28 |  |  | 3
46 |  | Viết Test Case |  |  | Dương | Low
47 |  | Integration Test |  |  | Dương | Medium
48 |  | System Test |  |  | Dương | High
49 |  | Regression Test |  |  | Dương | High
50 | UAT |  |  |  | Dương | Medium
Note on D1: admin: Size: 20
Note on L1: admin: Size 12

## Master
MASTER DATA
PIC | Status | Progress | Priority
Dương | Open | 0% | High
| In-progress | 10% | Medium
| Delay | 20% | Low
| Pending | 30%
| Done | 40%
50%
60%
70%
80%
90%
100%

## Copy of Sheet1 (hidden)
Low | To Do | All | Sprint | Month
Medium | Doing | Thiện | 0.3 | 0.6 | 1.8 | 4.8h
High | Done | Bình
|  | Hà | 0.3 | 0.6 | 1.8
|  | Trường | 0.5 |  | 0.5
|  | Nga |  |  | 1.5
|  | Huy |  |  | 5.6
Quỳnh
Binhvl